28/04/2020
Curriculum reviewing
Methodology proposal
04/05/2020

---
Objectives of this meeting
Objectives
To validate the objectives of the curriculum reviewing
- To validate the quest reviewing
- To propose the protocol for the methodology adopted
To discuss a work schedule milestones

---
Objectives of the curriculum reviewing
- To ensure a global coherence of our curriculums
- To align the content with the skill book (REAC)
- To list content available
- To identify the problems (quests mostly but also course, live coding, dojos, quizz, etc...)
- To correct problems and update quests
- To create content if missing
- To follow up the translation English/French

---
Methodology
Methodology
4. Update or create new content
Deliverable: updated quests or new quests in Odyssey
Teaching notes for other material
Program updated with the links to the resources
Deliverable:
- Update or creation of quests in Odyssey
- Teaching notes for other resources in Github
uploaded in Drive and Program
- Program(Curiculum) updated
Check curriculum and skill book
Those documents already exist:
- From the skillbook list the weeks where introduced
- Check if some are missing
- Check if some are not required
2. List existing content
Deliverable: first sheet of the Google sheet (Content reviewing)
Deliverable:
- Recollection and inventory in a github repository (avoid multiple versions, collaboration between teachers)
- Normalization of the content name files and folders (avoid duplicates, content organisation )
- References by week
- Global listing
3. Analyze content and identify content to be reviewed
Deliverable: 2nd sheet of the Google sheet (Content reviewing)
Content production Calendar
Deliverable:
- Content reviewing using templated issue labellised to updated priority creation
- Milestones and delivery date given inventory for production/update

---
Methodology, STEP1: Check curriculum and skill book
Methodology, STEP1: Check curriculum and skill book
Check coherence between skill book and curriculum
Understand (and get into) the detailed curriculum
(example, Data program)
Check the skill book
(example Skill book Data)

---
Methodology, STEP 2: List of existing content
Methodology, STEP 2: List of existing content
Teaching material is linked to the program (example, Data program)
- Quests (Odyssey)
- Courses: Google Drive
- Dojos, live coding, workshop: portal or Github
- Projects:
- Dev portal:
https://sites.google.com/wildcodeschool.fr/wcs-php-5m-program/accueil#h.p_1g8indUnrcZC
https://github.com/WildCodeSchool/js-training-materials
- Data: some slides in Google
- Checkpoints: Google Drive or portal
- Quizz: Kahoot
- Hackathon
- QuestsTalks & Masterclasses recordings

---
Methodology, STEP 2: List of existing content
Methodology, STEP 2: List of existing content
Check that all content is listed (highlight missing content)
Fill in the first sheet of the Google sheet (Content reviewing)
  - For each week:
    - Complete the week objectives
    - Describe the skills to be acquired
    - Add the corresponding reference of the skill (skill book)
    - Add all the teaching material: quests, dojos, etc and their objective
Highlight problems you identify

---
Analyze quests
Methodology, STEP 3: Analyze content
Analyze quests
- What is a good quest? (check this document)
- For each week, do the quests as if you were a student
- Analyze each quest (as if you were a student)
- Fill-in this second sheet of the Google sheet (Content reviewing)

---
Analyze other material (dojos, live coding, workshop)
Methodology, STEP 3: Analyze content
Analyze other material (dojos, live coding, workshop)
- List the material or activities missing for each week
- Identify the teaching notes missing
- Identify problems (if any)

---
Create a content production calendar
Work schedule
Create a content production calendar
Example for Deutsche Telekom
https://docs.google.com/spreadsheets/d/1G6wp3YJenK6zIfjhCp4Jbu-RS0TV3V2V_DudLrLIQMk/edit?usp=sharing
The calendar should include:
- The deadline for the technical proofreading
- The deadline for the translation proofreading

---
Methodology, STEP 4: Update or create content
Methodology, STEP 4: Update or create content
- Update quests on Odyssey
- or create missing ones on Odyssey
- List the new quests to be translated (and proofreading)
- Fill-in the teaching notes missing (see the model)
- Update the program with the new links (Data program)

---
Work schedule
Work schedule
Steps	Description	Deliverables	Deadline
STEP1	Check coherence between curriculum and skill book		12/05/2020
STEP 2	List of existing content	1 sheet of Google doc (content review)	13/05/2020
STEP 3	Analyze content (first 50 quests)	2nd sheet of Google doc (content review) for the 50 first quests	5/06/2020
STEP 3	Analyze content (next 50 quests)	2nd sheet of Google doc (content review) for the 50 last quests	30/06/2020
STEP 4	Content production calendar	Calendar	30/06/2020
STEP 4	Quests update + teaching notes (50 first)	Quests on Odyssey + teaching notes	31/07/2020
STEP 4	Quests update + teaching notes (50 last)	Quests on Odyssey + teaching notes	31/08/2020